# Executive Summary

We need to finish Phase 1 of the LMS: implement the remaining ~44 APIs and 12 UIs using real DB data, with multi-tenancy, RBAC and audit in place. Key tasks: Academic (classes/cohorts, sessions, attendance, catch-up), Ops (tickets, SLA, escalation), Finance (fee plans, invoices/payments/refunds+approvals), plus assets and governance UIs. Everything must respect centerId from session, role checks, and write AuditEvent on changes.

## 1. Implementation Checklist (Phase 1)

- Governance foundation: AuditLog + ApprovalRequest models (done) ✔️. Ensure all writes use lib/audit.ts; add RBAC/tenancy guards (e.g. requireRole, centerId=ctx.session.centerId).

- Academic: CRUD ClassCohort + ClassMembership; schedule/cancel Session; bulk Attendance marking (PRESENT/ABSENT → generate CatchUpPackage). Tutor “My Day” API = today’s sessions + pending attendance. Student “Catch-up” UI.

- Ops: CRUD Ticket (with comments/attachments); calculate slaDueAt from SLAConfig on create; add escalation job (cron) to mark overdue tickets as ESCALATED.

- Finance: CRUD FeePlan (FINANCE_ADMIN only); Invoice (+InvoiceLine) creation and listing; record Payment; Refund requests (status=PENDING) must create ApprovalRequest; approve/reject via Governance API.

- Infrastructure: CRUD Asset & MaintenanceEvent (optional for Phase1, UI under Admin/Infra).

- UI Pages: Tutor: My Day + Attendance screen; Student: Dashboard + Catch-up list; Supervisor/Reception: Ticket list/detail; Admin/Finance: Invoice list/detail + refund request/approval; Admin/Governance: Approvals queue + Audit log.

- Tests: Playwright E2E and API: verify tenancy isolation (no cross-center data), RBAC (denied where appropriate), flows (attendance→catch-up, invoice sums, SLA escalation).

## 2. Prisma Schema Changes

We already added new models (see schema): ClassCohort, ClassMembership, Session (linked to ClassCohort), AttendanceRecord, CatchUpPackage, Ticket/Comment/Attachment, SLAConfig, FeePlan, StudentAccount, Invoice/Line, Payment, Refund, plus related enums. Add composite indexes per domain (e.g. @@index([centreId, status]) on most). After editing prisma/schema.prisma, use npx prisma db:push. Ensure rollback plan (DB snapshots) for production.

For example, we see in schema: AttendanceRecord holds status and links to CatchUpPackage[1][2]. New indexes: e.g. (Session(centreId, startDate) for MyDay queries; Ticket(centreId,status,slaDueAt) for SLA).

## 3. API Contract (Phase 1)

Define REST endpoints (all in app/api/* with NextAuth session auth):

| Endpoint | Method | Auth Roles | Request Body / Query | Response | Errors (400/403/404/500) |
| --- | --- | --- | --- | --- | --- |
| /api/classes | GET | TEACHER,ADMIN,SUPER | — (scoped to session.center) | list of ClassCohort | 403, 500 |
| /api/classes | POST | TEACHER,CENTER_ADMIN | {name,subject,startDate,...} | created ClassCohort | 400, 403 |
| /api/classes/[id] | PUT | TEACHER,CENTER_ADMIN | {fields...} | updated ClassCohort | 400,403,404 |
| /api/classes/[id] | DELETE | TEACHER,CENTER_ADMIN | — | 204 No Content | 403,404 |
| /api/classes/[id]/members | GET | TEACHER,ADMIN,STUDENT/FAMILY (only self) | — | list ClassMembership | 403,404 |
| /api/classes/[id]/members | POST | CENTER_ADMIN,CENTER_SUPER | {studentId} | new ClassMembership | 400,403 |
| /api/sessions | GET | TEACHER,ADMIN,STUDENT | filter by date/class | list of Session | 403 |
| /api/sessions | POST | TEACHER,ADMIN | {classId, date, time,...} | created Session | 400,403 |
| /api/attendance | POST | TEACHER | [{sessionId,studentId,status},…] | {updated records} | 400,403 |
| /api/catchups | GET | STUDENT | — (auto-filter own center) | list of CatchUpPackage | 403 |
| /api/tickets | GET | SUPPORT,ADMIN,STUDENT | status, type filters | list of Ticket | 403 |
| /api/tickets | POST | ALL (even Student) | {subject,type,desc,priority} | created Ticket | 400 |
| /api/tickets/[id]/assign | POST | SUPPORT,ADMIN | {assignedToId} | updated Ticket | 400,403,404 |
| /api/tickets/[id]/comments | POST | ALL | {text,isInternal} | created TicketComment | 403,404 |
| /api/fin/fee-plans | GET/POST/PUT/DEL | FINANCE_ADMIN,CENTER_ADMIN | as needed | FeePlan | ... |
| /api/fin/invoices | GET/POST | FINANCE_ADMIN | {studentId, lines…} | Invoice | 400,403 |
| /api/fin/payments | POST | FINANCE_ADMIN | {invoiceId,amount,...} | Payment | 400,403 |
| /api/fin/refunds | POST | ANY (REQUEST), FINANCE_ADMIN (APPROVE) | {paymentId,reason,...} | Refund (status=PENDING) | 400 |
| /api/fin/refunds/[id]/approve | POST | FINANCE_ADMIN | — | Refund status=APPROVED | 403,404 |
| /api/governance/approvals | GET/POST/PUT | CENTER_ADMIN, SUPER_ADMIN | — | ApprovalRequest list/create | 400,403 |
| /api/governance/audit | GET | CENTER_ADMIN,SUPER_ADMIN | filters by user/date | audit events list | 403 |

(Note: All APIs auto-scope by session.centerId internally. See lib/rbac.ts for role checks.)

## 4. Frontend Routes & Components

Route map (with key components/pages):
- Tutor Dashboard /dashboard/tutor: My Day: card/list of today’s Classes→Sessions. - Attendance Page /class/[id]/attendance: table of students, attendance status (P/L/A). - Student Dashboard /dashboard/student: Enrolled Classes + Catch-Up Queue: list of pending catch-ups (title, dueDate, resources). - Supervisor/Tutor /dashboard/tickets: ticket list (filter by status/priority) + detail view (subject, comments). (Also integrated via /support or /admin sections.) - Finance /dashboard/finance/invoices: list of invoices with status (Paid/Overdue); detail page with lines, payment entry; refund request button. - Admin/Infrastructure /admin/assets: asset inventory list (ID, type, status); asset detail form; maintenance log. - Admin/Governance /admin/approvals: queue of ApprovalRequests (type, requestor); approve/reject actions; /admin/audit: searchable audit log table.

Components & UX notes: use accessible components (table with aria-sort, form with label, etc). Status badges (green=Completed, red=Pending, yellow=Overdue). Steps include loading skeletons and empty states (“No records.”). All forms require client-side validation (zod schemas).

## 5. Seed Data Expansion

Create 2 centers (e.g. “Center A”, “Center B”) with slug. For each: - Users: SUPER_ADMIN (global), each Center: 1×CENTER_ADMIN, 1×CENTER_SUPERVISOR, 1×FINANCE_ADMIN, 2×TEACHER, 1×ASSESSOR, 2×PARENT (each with 1-2 child students), 5×STUDENT. - Courses: 2 courses per center, with modules/lessons (to test enrollment links). - Classes/Cohorts: 2 classes (Active) per center, each taught by a different teacher, with 5 students enrolled (ClassMembership). - Sessions: for each class, 3 sessions (1 in past, 1 today, 1 future). Mark some attendance: few ABSENT to trigger catch-ups. - Catch-up: auto-generated for each absent in seed. (Manually insert or let background process.) - Tickets: 3 tickets per center with variety of type/priority; one escalated (set old createdAt to simulate delay). - SLAConfig: one per priority/type to allow slaDueAt calc. - Fee Plans: 1 per center; Invoices: 2 per center (one PAID, one PARTIAL); Payments: record payments to test balance; Refund: one pending (create ApprovalRequest). - Assets: 5 per center (some status Active/Broken); MaintenanceEvents: couple linked to tickets.

Seed script should upsert by unique fields to be idempotent. E.g. await prisma.user.upsert({ where: { email }, create: {...}, update: {...} }). At end, print a summary: Center slugs, user login creds.

## 6. Playwright Test Suite Plan

- Authentication: Save storageState for each role via API (login once).

- Tenancy Isolation: Test that Center A user cannot see Center B’s classes/tickets (expect 403 or empty).

- RBAC: Using each role state, attempt restricted actions. E.g. STUDENT cannot POST to /api/tickets/assign; expect 403.

- Academic Flow: Mark a session attendance as ABSENT (API or UI); verify a CatchUpPackage is created (/api/catchups returns it), and student sees it. Complete catch-up (via API) marks status, test overdue triggers.

- Finance: Create invoice with lines (via API); check subtotal/total. Record payment; ensure balance updates and invoice status changes to PARTIAL/PAID. Create refund request; verify approval needed to transition to APPROVED.

- Ticket/SLA: Create new ticket of type/priority; check slaDueAt = createdAt + config. Simulate time travel or run escalation job; test status becomes ESCALATED.

- Use Playwright fixtures to hit APIs (e.g. request.post(...)) and End-to-End to click through major flows. Write tests in tests/ with jest matcher (or Playwright Test).

Example test snippet:

// Verify RBAC: parent cannot see finance endpoint
test('Parent cannot access finance', async ({request, storageStateParent}) => {
  const r = await request.get('/api/fin/invoices', { headers: { cookie: storageStateParent.cookie } });
  expect(r.status()).toBe(403);
});

## 7. Background Jobs

- Catch-up Generation: Already triggered upon marking attendance ABSENT. To ensure reliability, run a nightly job (scripts/generateCatchups.ts) scanning all AttendanceRecord marked ABSENT without CatchUpPackage, create them (expiry = +7d).

- SLA Escalation: Cron job (scripts/escalateTickets.ts) daily: find Tickets where now > slaDueAt && status!=RESOLVED/CLOSED; set status=ESCALATED, write AuditEvent (action=ESCALATE).

- Deploy via system cron or serverless schedule. Log outcomes and email admins for escalations.

flowchart LR
    A((Attendance: ABSENT)) --> B[Generate CatchUpPackage (status=PENDING)]
    B --> C{CatchUp Due?}
    C -->|Completed by student| D[status=COMPLETED]
    C -->|Overdue| E[Supervisor notified / Escalate]
    E --> F[Optional: Create ApprovalRequest for extension]

gantt
    title Phase 1 Development Timeline
    dateFormat  YYYY-MM-DD
    section Governance 
    RBAC & Audit Engine       :done, 2026-03-01, 3d
    section Academic 
    Classes & Membership API  :done, 2026-03-04, 5d
    Sessions & Attendance     :done, 2026-03-09, 5d
    Catch-up Logic            :done, 2026-03-14, 3d
    section Operations
    Tickets API               :done, 2026-03-17, 4d
    SLA & Escalation Job      :done, 2026-03-21, 3d
    section Finance
    Invoices & Payments       :done, 2026-03-24, 4d
    Refund Workflow           :done, 2026-03-28, 3d
    section Finalize
    Testing & QA              :2026-04-01, 5d
    Deployment & Review       :2026-04-06, 2d

## 8. Deployment & QA Checklist

- Run npm run db:push (or migrate) to apply schema changes to staging.

- Seed fresh data as per plan.

- CI: Build + npm run test:e2e on PRs.

- Smoke test on https://lms.gagneet.com: sanity check login per role, key pages.

- Ensure ESLint and Prettier pass (including jsx-a11y rules[3]).

- Conduct performance scan (API load test) and security scan (OWASP).

- Backup DB before prod deploy; plan rollback path (Prisma backup, code revert).

## 9. Risks & Mitigations

- Tenant-data leaks: Risk: Query without centerId. Mitigation: All ORM calls use where: { centerId: session.centerId }; add tests to catch leaks. Consider Postgres RLS later.

- Approval bypass: Risk: Sensitive actions bypass approval. Mitigation: Audit logs + code review ensure critical paths use ApprovalRequest (e.g. refunds).

- Data loss: Risk: Drop relations inadvertently. Mitigation: Use soft deletes or status flags, backup before migrations.

- Scalability: Risk: Overloading single region. Mitigation: Design stateless + use CDN, plan multi-AZ DB as per docs (📝Deployment.md).

## 10. ADRs (Assumptions)

- Catch-up packages auto-generated on ABSENT; no manual opt-out.

- Refunds initially manual workflow, no auto-capture.

- If multiple tutors available on cancel, reassign by supervisor manually (no auto-match engine yet).

- Use server cron for background jobs (no real-time queue in Phase 1).

Citations: We rely on our schema (Prisma) for core models[1][2] and Next.js docs for accessibility best-practices[3]. These guide our design and ensure the implementation is consistent with standards.

[1] [2] schema.prisma

https://github.com/gagneet/learning-management-system/blob/851cd99af8e712a512e65cc15c4823d93c0a14ad/prisma/schema.prisma

[3] Architecture: Accessibility | Next.js

https://nextjs.org/docs/architecture/accessibility